Work Breakdown Structure (WBS) & Timeline Plan\

Project: Marketing Website Update

Prepared for: Marketing & IT Stakeholders

Date:12/20/2025

1. Introduction

This document outlines the Work Breakdown Structure (WBS) and timeline planning for the Marketing Website Update project. It breaks the project into phases, deliverables, and tasks, including estimated effort and dependencies. This plan supports execution, tracking, and stakeholder alignment.

2. Work Breakdown Structure (WBS)

1. Discovery & Requirements (2–3 Weeks)

| WBS ID | Task Name | Owner | Estimated Effort | Dependency |
| --- | --- | --- | --- | --- |
| 1.1 | Project kickoff & stakeholder alignment | Project Manager | 1 day | Project approval |
| 1.2 | Current website & analytics review | UX / SEO | 3 days | 1.1 |
| 1.3 | Stakeholder & user interviews | UX | 4 days | 1.1 |
| 1.4 | Content audit & gap analysis | Content | 3 days | 1.2 |
| 1.5 | Technical assessment (CMS & hosting) | Development | 3 days | 1.2 |
| 1.6 | SEO audit & baseline metrics | SEO | 2 days | 1.2 |
| 1.7 | Requirements documentation & sign-off | Project Manager | 3 days | 1.3–1.6 |

2. UX/UI Design (4 Weeks)

| WBS ID | Task Name | Owner | Estimated Effort | Dependency |
| --- | --- | --- | --- | --- |
| 2.1 | Information architecture & sitemap | UX | 4 days | 1.7 |
| 2.2 | Wireframes & user flows | UX | 6 days | 2.1 |
| 2.3 | Visual design & branding updates | UI | 8 days | 2.2 |
| 2.4 | Responsive design (desktop/mobile) | UI | 6 days | 2.3 |
| 2.5 | Accessibility design review (WCAG 2.1 AA) | UX | 3 days | 2.4 |
| 2.6 | Design review & revisions | UX/UI | 5 days | 2.5 |
| 2.7 | Final design approval | Stakeholders | 1 day | 2.6 |

3. Development & CMS Build (6–8 Weeks)

| WBS ID | Task Name | Owner | Estimated Effort | Dependency |
| --- | --- | --- | --- | --- |
| 3.1 | CMS setup / upgrade | Backend Dev | 5 days | 2.7 |
| 3.2 | CMS content model & modular blocks | Backend Dev | 6 days | 3.1 |
| 3.3 | Front-end development (homepage) | Frontend Dev | 6 days | 2.7 |
| 3.4 | Front-end development (landing pages) | Frontend Dev | 8 days | 3.3 |
| 3.5 | Navigation & IA implementation | Frontend Dev | 3 days | 3.3 |
| 3.6 | Mobile responsiveness | Frontend Dev | 4 days | 3.4 |
| 3.7 | Technical SEO implementation | SEO / Dev | 4 days | 3.4 |
| 3.8 | Performance optimization | Development | 3 days | 3.6 |
| 3.9 | Analytics & tracking setup | Analytics | 2 days | 3.8 |
| 3.10 | Content migration | Content | 6 days | 3.2 |

4. QA & User Acceptance Testing (3 Weeks)

| WBS ID | Task Name | Owner | Estimated Effort | Dependency |
| --- | --- | --- | --- | --- |
| 4.1 | Functional testing | QA | 4 days | 3.10 |
| 4.2 | Cross-browser & device testing | QA | 3 days | 4.1 |
| 4.3 | Performance testing | QA | 2 days | 4.2 |
| 4.4 | Accessibility testing | QA | 3 days | 4.2 |
| 4.5 | SEO validation | SEO | 2 days | 4.3 |
| 4.6 | Bug fixes & regression testing | Dev / QA | 6 days | 4.1–4.5 |
| 4.7 | Marketing UAT & approval | Marketing | 3 days | 4.6 |

5. Launch (1 Week)

| WBS ID | Task Name | Owner | Estimated Effort | Dependency |
| --- | --- | --- | --- | --- |
| 5.1 | Production readiness check | PM / Dev | 1 day | 4.7 |
| 5.2 | Backup & rollback plan | Development | 1 day | 5.1 |
| 5.3 | Website go-live | Development | 1 day | 5.2 |
| 5.4 | Smoke testing | QA | 1 day | 5.3 |
| 5.5 | Launch communication | Marketing | 1 day | 5.3 |

6. Post-Launch Monitoring (2 Weeks)

| WBS ID | Task Name | Owner | Estimated Effort | Dependency |
| --- | --- | --- | --- | --- |
| 6.1 | Performance & uptime monitoring | Development | 4 days | 5.3 |
| 6.2 | SEO tracking & indexing checks | SEO | 4 days | 5.3 |
| 6.3 | Analytics dashboard validation | Analytics | 3 days | 5.3 |
| 6.4 | CMS training for Marketing | PM / Content | 2 days | 5.3 |
| 6.5 | Project closure & handover | Project Manager | 2 days | 6.4 |

3. High-Level Gantt Chart Timeline

| Phase | Start Date | End Date |
| --- | --- | --- |
| Discovery & Requirements | Feb 1 | Feb 21 |
| UX/UI Design | Feb 22 | Mar 21 |
| Development & CMS Build | Mar 22 | May 20 |
| QA & UAT | May 21 | Jun 10 |
| Launch | Jun 11 | Jun 18 |
| Post-Launch Monitoring | Jun 19 | Jul 3 |

### Key Milestones

- Requirements Approved – Feb 21

- UX/UI Approved – Mar 21

- Development Complete – May 20

- UAT Sign-off – Jun 10

- Website Live – Jun 18

- Project Closure – Jul 3