PROJECT CHARTER – Marketing Website Update

1. Project Purpose / Problem Statement

The current marketing website is outdated in design, slow to load, and not fully mobile-optimized. The CMS limits Marketing’s ability to update content independently, causing delays in campaigns. SEO performance has declined, impacting visibility and lead generation. A modernized website is needed to improve user experience, strengthen brand presence, and support upcoming marketing initiatives.

2. Project Goals & Objectives

Goals

- Modernize the design and user experience.

- Improve website speed, accessibility, and SEO.

- Enable Marketing to manage and publish content independently.

Objectives

- Reduce page load time to <2.5 seconds.

- Improve organic visibility by 15% within 3 months of post-launch.

- Increase conversion rate on key pages by 10%.

- Reduce content publishing time from 48 hours to same-day updates.

3. Scope

In Scope

- Homepage and landing page redesign.

- Updated branding, UI components, and visual styles.

- Improved information architecture and site navigation.

- CMS upgrade/migration with modular content blocks.

- Technical SEO improvements and cleanups.

- Mobile responsiveness, accessibility (WCAG 2.1 AA), and QA testing.

- Updated analytics and tracking.

Out of Scope

- E-commerce functionality.

- Backend systems are not related to CMS.

- New product microsites.

- Multi-language support (future phase).

4. Stakeholders

- Project Sponsor: Chief Marketing Officer

- Business Owner: Marketing Director

- Project Manager: IT Project Manager

- Core Team: UX/UI, Front-End Dev, Back-End Dev, QA, SEO, Content

- External Partners: Design/UX agency (if required)

5. Deliverables

- Approved UX/UI design prototypes.

- Fully updated and responsive marketing website.

- Upgraded CMS with reusable content modules.

- SEO optimization is implemented.

- Performance, accessibility, and QA test results.

- UAT approval from Marketing.

- Launch and rollback plan.

- Post-launch analytics dashboard/report.

6. High-Level Timeline

| Phase | Duration | Estimated Dates |
| --- | --- | --- |
| Discovery & Requirements | 2–3 weeks | Feb 1 – Feb 21 |
| UX/UI Design | 4 weeks | Feb 22 – Mar 21 |
| Development & CMS Build | 6–8 weeks | Mar 22 – May 20 |
| QA & UAT | 3 weeks | May 21 – June 10 |
| Launch | 1 week | June 11 – June 18 |
| Post-Launch Monitoring | 2 weeks | June 19 – July 3 |

7. Success Criteria

- Website launched with no P1/P2 defects.

- Page load speed meets target (<2.5 seconds).

- SEO and conversion improvements are achieved as planned.

- Marketing is fully self-sufficient in using the CMS.

- Stakeholder satisfaction is ≥90%.

- Meets accessibility and mobile optimization standards.